## Variation-Adjusted BOQ
BILL OF QUANTITIES (VARIATION-ADJUSTED) — Dammam Logistics Park
Contractor: Eastern Province Steel Works Co. ¦ Currency: SAR ¦ Adjusted BOQ as of: 30-Jun-2026 (incorporates VO-DLP-003, 007, 009, 011)
Item No. | Description | Unit | Quantity | Rate (SAR) | Amount (SAR) | Note
1.1 | Site clearance and earthworks | m2 | 42000 | 38 | 1596000
1.2 | Excavation for foundations | m3 | 22800 | 65 | 1482000 | Adjusted per Variation Order
1.3 | Backfilling and compaction | m3 | 12300 | 42 | 516600
2.1 | Reinforced concrete - pile caps | m3 | 3200 | 850 | 2720000
2.2 | Reinforced concrete - ground slab | m3 | 5400 | 720 | 3888000
2.3 | Structural steel frame - primary members | ton | 2850 | 6850 | 19522500 | Adjusted per Variation Order
2.4 | Structural steel frame - secondary members | ton | 1120 | 6400 | 7168000 | Adjusted per Variation Order
3.1 | Metal roof cladding system | m2 | 28000 | 145 | 4060000
3.2 | Wall cladding - insulated panels | m2 | 19500 | 168 | 3276000
4.1 | Warehouse floor - reinforced concrete with hardener | m2 | 36000 | 210 | 7560000
5.1 | External paving and hardstanding | m2 | 18500 | 95 | 1757500 | Adjusted per Variation Order
6.1 | Fire protection system - sprinklers (ESFR) | sum | 1 | 4750000 | 4750000 | Adjusted per Variation Order
6.2 | Electrical distribution and lighting | sum | 1 | 5600000 | 5600000
7.1 | Stormwater drainage network | m | 3400 | 320 | 1088000
8.1 | Additional dock leveler installation (12 no.) - VO-DLP-009 | no. | 12 | 68000 | 816000 | New item added by Variation Order
8.2 | Extended perimeter security fencing - VO-DLP-011 | m | 850 | 410 | 348500 | New item added by Variation Order
TOTAL VARIATION-ADJUSTED VALUE |  |  |  |  | 66149100
Original Contract Value (SAR) — Source: Dammam_Logistics_Park_BOQ_Original.xlsx |  |  |  |  | 61963100
Cost Slippage (Adjusted - Original): |  |  |  |  | 4186000