REQUEST FOR INFORMATION (RFI) LOG

Al-Faisaliah Tower Renovation — MEP Subcontractor: Al-Faisaliah MEP Systems LLC

Log maintained by: Main Contractor Document Control Office

Last updated: 28 June 2026

| RFI No. | Subject | Raised By | Date Raised | Status | Response Due |
| --- | --- | --- | --- | --- | --- |
| RFI-MEP-041 | Clarification on chiller plant room ventilation duct routing vs. structural beam clash at Level B2 | Al-Faisaliah MEP Systems LLC | 02-May-2026 | OPEN | 16-May-2026 (OVERDUE) |
| RFI-MEP-042 | Fire-rated damper schedule discrepancy between MEP-401 and Architectural door schedule | Al-Faisaliah MEP Systems LLC | 09-May-2026 | OPEN | 23-May-2026 (OVERDUE) |
| RFI-MEP-043 | توضيح بخصوص مسار مواسير التكييف في الطابق الميكانيكي وتعارضها مع الكمرات الإنشائية | Al-Faisaliah MEP Systems LLC | 14-May-2026 | OPEN | 28-May-2026 (OVERDUE) |
| RFI-MEP-044 | Voltage drop calculation request for standby generator feeder — Panel DB-G1 | Al-Faisaliah MEP Systems LLC | 20-May-2026 | CLOSED - Response Issued 30-May-2026 | 03-Jun-2026 |
| RFI-MEP-045 | طلب توضيح حول مواصفات مضخات مكافحة الحريق البديلة المقترحة من المورد | Al-Faisaliah MEP Systems LLC | 02-Jun-2026 | OPEN | 16-Jun-2026 (OVERDUE) |
| RFI-MEP-046 | Request to confirm BMS integration protocol (BACnet vs Modbus) for chiller plant controls | Al-Faisaliah MEP Systems LLC | 10-Jun-2026 | OPEN | 24-Jun-2026 (OVERDUE) |
| RFI-MEP-047 | Coordination clash: cable tray route vs. new structural bracing added per SI-014 | Al-Faisaliah MEP Systems LLC | 18-Jun-2026 | OPEN | 02-Jul-2026 (OVERDUE) |
| RFI-MEP-039 | Domestic water booster pump set — confirm duty/standby configuration | Al-Faisaliah MEP Systems LLC | 11-Apr-2026 | CLOSED - Response Issued 22-Apr-2026 | 25-Apr-2026 |

Summary: 6 RFIs currently OPEN (5 overdue against original response due date), 2 CLOSED. All open items relate to MEP coordination clashes and equipment confirmation pending Engineer response.