## VO Log
VARIATION ORDER LOG — Riyadh Heights Residential Towers
Main Contractor: Al-Rashid Construction Est. ¦ Currency: SAR ¦ Log as of: 30-Jun-2026
VO No. | Description | Raised By | Category | Date Approved | Cost Impact (SAR) | Time Impact (days) | Status
VO-001 | Additional basement waterproofing due to elevated groundwater table found during excavation | Main Contractor | Site Condition | 15-Mar-2024 | 1250000 | 12 | APPROVED
VO-002 | Upgrade to podium level facade cladding per Client's revised aesthetic brief | Client | Client Change | 02-May-2024 | 3800000 | 25 | APPROVED
VO-003 | Relocation of main electrical substation due to civil defense access-road requirement | Civil Defense / Municipality | Statutory | 20-Jul-2024 | 970000 | 18 | APPROVED
VO-004 | Omission of originally-specified swimming pool deck heating system | Client | Client Change | 11-Sep-2024 | -420000 | 0 | APPROVED
VO-005 | Additional pile testing (2 no. static load tests) requested by geotechnical consultant | Consultant | Design Development | 05-Nov-2024 | 310000 | 8 | APPROVED
VO-006 | Upgrade of fire pump set capacity per revised Civil Defense hydraulic calculation review | Civil Defense | Statutory | 14-Jan-2025 | 640000 | 10 | APPROVED
VO-007 | Additional structural steel bracing to Tower B roof due to updated wind load code | Consultant | Design Development | 22-Mar-2025 | 890000 | 15 | APPROVED
VO-008 | Client-requested upgrade to lobby finishes — marble flooring in lieu of specified porcelain | Client | Client Change | 18-May-2025 | 1140000 | 20 | APPROVED
VO-009 | MEP re-routing to accommodate revised retail unit layout on Ground Floor | Client | Client Change | 09-Aug-2025 | 560000 | 14 | APPROVED
VO-010 | Extended dewatering works due to unseasonal rainfall during basement construction | Main Contractor | Site Condition | 27-Oct-2025 | 480000 | 21 | APPROVED
VO-011 | Additional CCTV and access control points per updated Client security brief | Client | Client Change | 12-Jan-2026 | 275000 | 5 | APPROVED
VO-012 | Facade sealant system upgrade following mock-up testing failure | Main Contractor | Quality/Defect Rectification | 08-Mar-2026 | 390000 | 9 | APPROVED
VO-013 | Proposed upgrade to elevator car finishes — under review, not yet priced | Client | Client Change | PENDING | 0 | 0 | PENDING PRICING
VO-014 | Additional signage package for parking basement wayfinding | Client | Client Change | 02-Jun-2026 | 165000 | 3 | APPROVED
TOTAL |  |  |  |  | 10450000 | 160
Total APPROVED cost impact (excl. pending items) |  |  |  |  | 10450000